## Sheet1
Asset | Risk | Desciption | Likelihood | Severity | Priority | Existing Controls | Recommended Mitigations | Residual Risk
Funds | Business Email Compromise | Employee tricked into sharing credentials | 3 | 2 | 6 | Basic email filtering User authentication with passwords | MFA Phishing awareness training | Medium
Funds | Compromised User Database | Unauthorized access to customer data | 2 | 3 | 6 | Basic database access control Limited encryption | Strong encryption at rest Role-based access control Regular security audits | Medium
Funds | Financial Records Leak | Backups publicly accessible | 2 | 3 | 6 | Periodic data backups | Secure backup storage Access control for backup servers | Low to Medium
Funds | Theft | Unlocked safe | 1 | 2 | 2 | Physical security procedures Employee presence | Locking mechanisms Access logging Regular physical security checks | Low
Funds | Supply chain disrpution | Natural Disasters | 1 | 1 | 1 | Multiple business partnerships | Business continuity planning Alternative suppliers Disaster recovery procedures | Low